Regio1st guide to create a

Stakeholder engagement plan

Co-funded by the European Union under project n°101076088. Views and opinions expressed are however those of the author(s) only and do not necessarily reflect those of the European Union or CINEA. Neither the European Union nor the granting authority can be held responsible for them.

Stakeholder engagement plan template

REGIO1st Planning Framework

Stage 2 - Engaging stakeholders and building partnerships.

https://fedarene.org/project/regio1st/

Date of last update:	30/11/2023

Release version: 2.0

Prepared by:

Institute of Communications and Computer Systems (ICCS), National Technical University of Athens	 (NTUA)

Contact:

Georgios S. Konstantopoulos, gkonstantopoulos@epu.ntua.gr

Contents

Introduction	3

Proposed Structure of a Stakeholder engagement plan	4

Instructions	5

Chapter 1: Objectives of the stakeholder engagement plan	5

Chapter 2: Stakeholder mapping and analysis	6

Chapter 3: Define potential involvement of each stakeholder	8

Chapter 4: Define engagement tools/ channels	9

Chapter 5: Schedule of related events	11

Chapter 6: Monitoring	12

Annex: Templates	13

Event agenda	13

Events disclaimers	15

Event report	16

Stakeholder Feedback survey	17

- Introduction

Welcome to the Stakeholder Engagement Plan template of the Regio1st Planning Framework, a comprehensive resource designed to empower organizations and individuals alike in fostering meaningful connections with those who have a vested interest in regional/local energy and climate planning.

Energy planning should involve several different stakeholders at different steps, thus multiple needs, interests, and conflicts emerge. Therefore, the ability to engage and collaborate effectively with stakeholders is essential for achieving and implementing a commonly accepted strategic planning.

This template outlines the essential parts of a successful stakeholder engagement plan including its’ purpose and objectives, as well as strategies for engaging with key stakeholders. Whether you are a regional/local authority, an energy agency, or an individual, this guide will help you navigate the intricate landscape of stakeholder engagement. From choosing a tailored engagement tools to mapping out your stakeholders and monitoring your progress, every essential step you need to take is proposed here. Finally, this template is designed to be complementary with the Stakeholder Identification and Analysis Tool, provided within the Regio1st Planning Framework, so you can use their results to draft parts of this plan.

- Proposed Structure of a Stakeholder engagement plan

An effective stakeholder engagement plan is designed to provide the essential path and considerations that will enable you to identify, understand, and engage with the diverse groups and individuals who have a vested interest in your project. By following a structured approach, you will be better equipped to build meaningful relationships, manage expectations, and navigate potential challenges that may arise during the course of implementing the EE1st principle in your energy planning.

The proposed stakeholder engagement plan comprises six key chapters that include all the needed ingredients for a meaningful stakeholder engagement:

Introduction

Introduction sets the context and purpose of the plan.

Chapter 1: Objectives of the stakeholder engagement plan

Chapter 1 elaborates on the objectives of the engagement plan, delineating its overarching goals and desired outcomes.

Chapter 2: Stakeholders mapping and analysis

Chapter 2 delves into stakeholder mapping and analysis, identifying key stakeholders and assessing their interests and influence.

Chapter 3: Define potential involvement of each stakeholder

Chapter 3 outlines the potential involvement of each stakeholder, specifying their roles and responsibilities.

Chapter 4: Define engagement tools/channels

Chapter 4 defines the engagement tools and channels to be utilized for effective communication and interaction.

Chapter 5: Schedule of related events

Chapter 5 presents a schedule of related events, detailing when and how engagement activities will take place

Chapter 6: Monitoring

Chapter 6 focuses on monitoring, providing mechanisms for tracking and evaluating the success of the engagement plan over time, ensuring its adaptability and responsiveness to changing stakeholder dynamics and needs.

- Instructions

- Chapter 1: Objectives of the stakeholder engagement plan

In this 1st chapter, the fundamental purposes behind the creation and implementation of a comprehensive stakeholder engagement plan are explored and presented. By giving the essential objectives to engage with various stakeholders effectively, regional/local authorities will have cleared the reasons why stakeholder engagement is crucial in the planning under EE1st principle. It could also highlight the specific benefits (effective communication, strong relationships, informed decision-making) that they can have from a well-structured engagement plan.

From the stakeholders’ perspective, a successful stakeholder engagement plan will enable them to provide valuable knowledge they have about the pilot regions and their decision-making structures, thus adjusting the use of the Regio1st framework’s tools based on their needs. This can be done by providing information on stakeholders’ preferences, investment possibilities and social cost-benefits evaluation. They will also contribute to the social acceptability and the viability of the investment trajectories features in the decision-support system.

Motivate stakeholders to engage!

Inform about the decision-making processes and cultures in their respective regions and influence (to different extents) towards the embedding of energy efficiency first principle, a matter of shared interest among them, as a decisive principle in regional planning and related investments.

- Chapter 2: Stakeholder mapping and analysis

In this chapter, the findings from the Stakeholder Identification and Analysis Step of the Regio1st Planning Framework should be thoroughly elaborated and visualized.

To begin, include the stakeholder mapping, which encompasses individuals, groups, or organizations identified through the Stakeholder Identification and Analysis Tool. You may choose to use a matrix or diagram to visually represent the stakeholders and their relationships.

The extent to which a stakeholder can impact the execution of a measure and the significance of this measure in fulfilling its objectives dictate the suitable mode of involvement for individual stakeholders throughout various project phases. These two factors, when graphed together, generate an "Importance-Influence Matrix." Consequently, each regional authority identifies four distinct stakeholder categories, each necessitating a tailored participation approach. It is crucial to continuously update and review your stakeholder map to accommodate any new stakeholders that emerge or changes in priorities.

Influence on the regional energy planning process HIGH LOW Interest in energy efficiency HIGH LOW

Figure 1 – Importance-Influence Matrix

Additionally, incorporate the stakeholder analysis and provide further details on the findings obtained using the "Stakeholder Identification and Analysis Tool".

During the analysis, it is essential to clearly define the roles, interests, relevance, influence, and potential impact of each stakeholder in the energy transition. This analysis helps in understanding the dynamics and power dynamics among stakeholders, enabling effective stakeholder engagement and management throughout the project.

In addition to the above analysis, it is important to summarize/synthesize the stakeholder analysis in a format that reveals potential areas of conflict and collaboration and the potential impact of each stakeholder, as illustrated in the tables below.

Table  1 – Example of a stakeholder mapping and analysis table in regional energy planning.

| Stakeholder | Role in implementation | Role in planning | Role in investment | Monitoring power |
| --- | --- | --- | --- | --- |
| Regulatory bodies | Address DSO/TSO remuneration, of tariffs and market design and rules for RES support | Take part in the development of demand-conscious cost-benefit analysis methodology | Responsible for the approval of network investment plans, checking them against EU and national plans | Run a compliance check and review TSO and DSO reporting |
| Electricity producers | Do forecasts, company strategies and investment plans | Make an assessment of investment alternatives in fuels and locations | Invest in power plants. For vertically integrated companies they take on the role of suppliers to consumers for energy efficiency actions | Run an internal monitoring of investment process and energy production and pricing |
| … | … | … | … | … |

Target audience/key stakeholders

After having completed the stakeholder mapping and analysis, you will be able to have a defined group of key stakeholders and target audience. A typical stakeholder mapping in the content of the implementation of the EE1st principle in regional and local planning includes at least:

- Regional and local authorities

- Regulatory bodies

- Grid system operators (TSOs/DSOs/)

- Electricity producers

- Citizens groups, consumers, businesses, associations

- Chapter 3: Define potential involvement of each stakeholder

In the stakeholder analysis's final stage, you have identified suitable stakeholders and highlighted the value proposition of the project to encourage their effective engagement in the regional planning activities.

In this chapter, the potential involvement of each stakeholder is defined according to the stakeholder analysis, as conducted in Step 2.1 using the "Stakeholder Identification and Analysis Tool". This tool provides tailored recommendations on their involvement, according to the Influence-Interest score indicated. These recommendations can be expanded according to the regional context and each stakeholder’s role. Engagement can encompass activities such as sharing information, enhancing capacity, collaborating on measures and initiatives, or potentially giving endorsement to certain actions.

More specifically, the type of potential involvement of stakeholders with regards to the design and implementation of the regional energy strategy under EE1ST principle, may include:

- Informing: Stakeholders can provide relevant information and insights related to the design and implementation of the regional energy strategy.

- Capacity building: Stakeholders can participate in capacity building workshops to enhance their understanding and skills regarding the EE1st principle and the energy planning procedure in local, regional and national level.

- Co-designing: Stakeholders can collaborate in the development of energy planning and decision making for the regional energy strategy, ensuring their perspectives, needs and expertise are incorporated.

- Evaluating: Stakeholders can contribute to the evaluation of the effectiveness and impact of the implemented decisions, providing valuable feedback for improvement.

- Supporting endorsement: Stakeholders, including utilities and other supportive/involved parties, can endorse and support the decisions made under the regional energy strategy.

Involvement table

To summarize the stakeholder involvement across different project stages, a table can be created to present the specific type of involvement for each stakeholder.

Table  2 – Example of a Stakeholder involvement indicative table

| Stakeholder | Engagement strategy | Value proposition | Communication method | Engagement event/activity | Planning Stage |
| --- | --- | --- | --- | --- | --- |
| … | … | … | … | … | … |
| … | … | … | … | … | … |
| … | … | … | … | … | … |

- Chapter 4: Define engagement tools/ channels

After having identified the potential level of engagement of each stakeholder, in this chapter you define the engagement tool(s) and channel(s) per stakeholder. This is an important part of the plan, as the success of the engagement heavily depends on an effective way of building and maintaining functional relationships with each stakeholder.

Various tools and channels are available for effective stakeholder engagement. These include:

- Meetings: Arrange face-to-face interactions with stakeholders, such as one-on-one (online) meetings, focus groups, or larger stakeholder assemblies.

- Workshops: Conduct collaborative problem-solving sessions, using interactive activities and group exercises to encourage meaningful discussions.

- Surveys and questionnaires: Collect structured feedback and perspectives from stakeholders through online or offline surveys.

- Interviews: Conduct individual interviews to delve into stakeholders' opinions, concerns, and suggestions in greater detail.

- Online platforms and forums: Utilize dedicated project websites, social media groups, newsletters or discussion forums for ongoing virtual engagement and information sharing.

- Focus groups: Bring together small groups of stakeholders with similar interests to discuss specific topics or issues in a facilitated setting.

- Public consultations: Organize open meetings or events where stakeholders and the public can contribute their input and feedback.

- Stakeholder advisory committees: Establish committees comprising representatives from different stakeholder groups to foster ongoing engagement and collaboration.

- Online collaboration tools: Employ shared documents, project management software, or virtual whiteboards to facilitate stakeholder collaboration and information sharing.

- Presentations and webinars: Deliver informative presentations or host webinars to update stakeholders on project progress and encourage interactive discussions.

Communicate meaningfully!

The implementation of the Regio1st Planning Framework’s stages requires regional workshops be organised to support the use of the decision-support tool. The regional stakeholders identified can be reached out to through existing communication channels established by the regional/local authority. In case where no pre-existing link between authority and identified stakeholders is established, authority should establish contact from an earlier stage (via mailing, phone communication or meetings to explain the project’s aim).

Citizens will be engaged throughout this task via the participatory design workshops mentioned above, at regional/local level. Citizens and consumers representatives will inform the discussions on the decision-support system on constraints and interests to be taken into account for the social acceptance of the new investment and planning models that will emerge as a result of the project.

- Chapter 5: Schedule of related events

In this chapter, the schedule of the stakeholders’ engagement events or activities are included. To create a successful schedule that works for all stakeholders, coordinate with them and select mutually agreeable dates and times for the engagement events. Be mindful of any time availability constraints, and other scheduling considerations. Online scheduling tools may help match availabilities of different stakeholders.

Select the most suitable format for the engagement events, considering factors such as the number of participants, their locations, and their preferred means of communication.

The name and contact details of the person(s) to approach and invite to participate/contribute to the different regional energy planning activities is useful to be identified for each key organization.

| Estimated date | Task | Organiser | Type of event | Participants/Audience (Stakeholders) |
| --- | --- | --- | --- | --- |
| … | … | … | … | … |
| … | … | … | … | … |
| … | … | … | … | … |

Event Agenda!

You can use an Event Agenda for effectively planning and organizing an event. The specific elements to include in an event agenda can vary depending on the type of event, its duration, and its goals. An event agenda template is provided in the Annex.

- Chapter 6: Monitoring

Monitoring is a vital part in a stakeholder engagement plan, as it enables you to track progress, assess effectiveness, and make informed adjustments to your engagement strategies. These elements help ensure that your engagement efforts remain aligned with your planning activities’ goals and that stakeholders are actively involved and satisfied with the process.

In this section, you can include the identified proper measures that monitor the stakeholder engagement in the planning under the EE1st principle. Monitoring in a stakeholder engagement plan may include data collection about stakeholder overall engagement experience, progress assessment of the engagement activities’ progress, feedback receiving by the stakeholders (concerns, suggestions for improvement), identification of issues or challenges, track the effectiveness of communication channels and messages used, identify potential risks in maintain thriving stakeholder relationships etc.

Feedback mechanisms

The engagement of the stakeholders in Task 3.2. will be reported through the event report template (available in the Annex).

If any micro-intervention takes place, this can be reported through the event template, whether they take place in the framework of the workshops mentioned above or as specific measures or techniques put in place by pilot regions to achieve these events’ objective and to mitigate obstacles/challenges identified through the engagement of stakeholders and citizens (whether through their participation to events or through the interviews).

- Annex: Templates

- Event agenda

(example)

Agenda

Title of event

[Date]

[Time]

[Location

Welcome (5-10 minutes)

- Introduction of facilitators and attendees.

- Brief overview of the purpose and objectives of the workshop.

Overview of the Regional Energy Planning status (20 minutes)

- Present an overview of the regional energy planning process or elaborate on the specific Planning Stage for which stakeholders are needed.

- Discuss the importance of stakeholder engagement in regional energy planning.

- Provide an overview of the current energy situation in the region.

- Present relevant key information (statistics, challenges, opportunities, trends etc)

Stakeholders’ Perspectives (40 minutes)

- Facilitate a discussion among stakeholders to gather their perspectives on regional energy planning (or the specific planning stage).

- Encourage participants to share their experiences, concerns, and ideas related to energy planning in the region.

Break (10-15 minutes)

Next Steps and Commitments (30 minutes)

- Summarize the key outcomes and perspectives generated during the workshop.

- Take decisions if requested by the planning stage.

- Discuss the next steps in the planning process.

- Invite participants to make commitments or express their willingness to contribute to the implementation of the energy plan.

Wrap-up and Closing Remarks (10 minutes)

- Provide a brief summary of the workshop proceedings and highlight any follow-up actions.

- Thank the participants for their valuable contributions.

Note: Τhe structure and the content of each event depend on the planning stage, the process, and the foreseen duration. The time allocated to each agenda item can be adjusted based on the workshop's overall duration and specific needs.

- Participants can be divided into small groups and assign each group a specific topic related to energy planning, according to the workshop content.

- Different methods of brainstorming and sharing experiences can be used, tailored to the planning stages and participants’ profile.  Instructions/facilitation for the co-creation method is strongly recommended.

- A framework or template for the groups to structure their discussions and ideas would be helpful.

- Encourage open discussion and feedback from all participants.

  - Events disclaimers

Online events

By registering to this event, I authorise [organization responsible for the event or project] to record the event and agree that such footage may be used to illustrate and promote the activities of [organization responsible for the event or project].

In-person events option 1

By registering to this event, I authorise [organization responsible for the event] to include my name in the list of participants and proceedings of the event. I grant [organization responsible for the event], its representatives and employees the right to photograph and/ or film my attendance at the event and agree that such images of me may be used to illustrate and promote the activities of [organization responsible for the event].

In-person events option 2

Before, during and after the event, photos will be taken, and video and audio recordings may be made. By registering, you declare your consent that [organization responsible for the event]  and the project partners may publish photo and video material for reporting purposes on their respective websites and in their publications, in the press and via online channels.

[Optional: If you do not agree with photo, video or audio recordings, we ask you to give us a note in writing before the event or - if the time does not allow it - to express your objection to the organizers on arrival at the venue]

By registering, you agree that we use and maintain the personal data you provided for the purpose of documentation, organization, realisation and follow-up of the event.

I agree that my name, business, position and contact details will be displayed on the participant list of the event.

I agree and am interested that [organization responsible for the event] will include me in its mailing list and inform me about future events, project and further activities.

Important

The aforementioned disclaimer templates are provided for informational purposes only and should be used as a general guideline. It is imperative to tailor this template to suit the specific requirements and nature of the workshop or event you intend to host. Additionally, it is essential to ensure compliance with the national laws and regulations governing data protection in the respective countries where the events will be held. We strongly advise seeking legal counsel or consulting relevant authorities to ensure full compliance with applicable laws and regulations.

- Event report

Event Report

Title of event

[Date]

[Time]

[Location

[Small description of the event]

Agenda

- 10h-12h:

- 12h-13h:

Participants

| Organisation | Name | Attendance |
| --- | --- | --- |

Outcomes

….

Next steps

The following outcomes and next steps have been agreed on:

| What | When | Who |
| --- | --- | --- |

- Stakeholder Feedback survey

Stakeholder Feedback Summary: Regional Energy Planning event

Date: [Date of the Workshop]

Location: [Workshop Venue]

Dear [Stakeholder's Name],

Thank you for participating in the Regional Energy Planning Workshop/Meeting/Discussion organized by [Your Regional Authority's Name]. Your valuable input and insights are vital for the development of our regional energy planning initiatives. To further enhance our collaboration and ensure effective engagement, we kindly request your feedback on the event.

Please take a few moments to provide any additional comments, suggestions, or concerns you may have regarding the workshop or regional energy planning in general.

Your feedback is crucial for us to improve our engagement efforts and develop effective regional energy planning strategies. We highly appreciate your time and dedication in contributing to this process.

Please submit your feedback by [Deadline for Submission] via [Preferred Feedback Submission Method]. If you have any questions or need further assistance, please do not hesitate to contact us at [Contact Information].

Thank you once again for your participation and support.

Best regards,

[Your Name]

[Your Title/Position]

[Your Regional Authority's Name]

[Contact Information]

(Further possible questions about the facilitation and content of the event)

Objectives:

Were the objectives of the workshop clearly communicated?

Any suggestions for improving the clarity or formulation of the objectives?

Content and Presentations:

Were the presentations informative and engaging and content relevant?

Were there any specific topics or areas that you would have liked to see addressed in more detail?

Discussions and Activities:

How would you rate the overall quality and effectiveness of the discussions and activities during the workshop?

Were there any discussion points or activities that stood out to you as particularly valuable or noteworthy?

Facilitation and Organization:

How would you rate the facilitation of the workshop?

Did the facilitators effectively manage time and encourage participation from all stakeholders?

Networking and Collaboration:

Were there any specific collaborative activities or initiatives discussed that you would be interested in participating in?

Any suggestions for enhancing networking and collaboration in future workshops or events?

Instead of sending a feedback email, as presented, you can use an online questionnaire asking for the participants’ feedback, to make the process more user friendly and less time consuming.

Quick tips Image: freepik