## Cover
Monitoring Template
REGIO1st Planning Framework
Stage 7 - Defining actions and developing the regional energy plan
https://fedarene.org/project/regio1st/
Date of last update | 2024-02-03
Version number | 2
Prepared by | ICCS
Contact | hneofytou@epu.ntua.gr
gkonstantopoulos@epu.ntua.gr
Co-funded by the European Union under project n°101076088. Views and opinions expressed are however those of the
author(s) only and do not necessarily reflect those of the European Union or CINEA. Neither the European Union nor the
granting authority can be held responsible for them.

## Instructions
Monitoring Template
User instructions
Guidance
Objective
The purpose of this template is to assist users in monitoring the implementation of the actions/interventions incorporated in their regional energy plan. It can enable planners report on progress and on the impact of actions/interventions and evaluate their effectiveness.
Description
The Monitoring template is a structured tool designed to support regional authorities in monitoring their progress regarding the implementation of each action in an efficient and comprehensive way. The tool provides tables, graphics and indicators to assist the procedure.
How do I use this tool?
(1) Actions Monitoring | This tab prompts the user to collect key data in order to effectively monitor selected actions of the regional plan. It helps define the current status of each action and quantify the indicators that will be used to monitor progress. Key performance indicators are already defined in the tab and the user can also addother indicators.
(2) Graphic Results | Once the first tab is filled with data, the tab "Graphic Results" presents the results graphically. More specifically there are 3 different figures that present the results in a more user-friendly way.
(3) Indicators | This tab provides an indicative list of indicators that can be used to monitor progress in implementing sustainable energy actions The user should choose the most suitable indicators (or add new ones) to use in the "Actions Monitoring" tab.
(4) Example | An example of monitored actions is presented, along with a graphical representation of the results.

## Actions Monitoring
Monitoring Template
Actions Monitoring
| Who: | Regional authority & planners
| What: | Name the actions to be monitored and collect data to monitor the actions (status, duration, impact etc.).
| How: | Fill in the following table with the planned actions of the region (as many actions as needed) - Click on the first column to select the current status of the action, using the drop-down list. - The information in the rest of the cells is filled in manually. This includes information defined for each action (e.g. budget and key performance indicators such as energy savings) at the planning stage, but also updated to reflect the present date. In order to fill in the last two columns, regarding additional indicators, an indicative list is provided in the tab "Indicators". The user can add as many columns as needed to report on extra indicators. It is recommended to monitor at least one additional indicator per action. The second table summarises the status of actions.
| Actions | Status (drop-down list) | Duration |  |  |  | Budget |  | Energy savings |  | Renewable Energy Sources (RES) |  | Other impacts (e.g. new jobs) | Main barriers (if any) | Indicators |  | Other comments | Is this action exemplar?
|  |  | Estimated start | Actual start | Estimated end date | Actual end date | Estimated budget (Euros) | Cost spent so far (Euros) | Energy savings targets (KWh) | Actual energy savings (KWh) | RES production targets (KWh) | Actual RES production (KWh) |  |  | Type of key indicator monitored | Achievement until now
Action 1 (type the action's name)
Action 2
Action 3
Action 4
Action 5
Action 6
Action 7
Action 8
Action 9
Action 10
Action 11
Action 12
Action 13
Action 14
Action 15
Total number of Actions
| Completed | 0
| Ongoing | 0
| About to start | 0
| Postponed for later | 0
| Future | 0
| Canceled | 0
| Total | 0

## Graphic Results
Monitoring Template
Results Visualisation
What: | The following figures provide a graphic analysis of the data entered in the tab "Actions Monitoring"

## Indicators
Monitoring Template
Indicative list of indicators
What: | The following table outlines numerous indicators that can be used to support the monitoring of the actions. The user may select any of these indicators (or add new ones) that are the most appropriate for the actions to be monitored. Selected indicators are used in the tab "Actions Monitoring"
Sector | Indicators | Measurement Unit
Buildings | Lamps replaced with LEDs (per building/total) | Number of lamps replaced
| Area covered with automations in lighting | m2
| Upgrades in cooling & heating systems | Number of new heating & cooling systems
| Insulation | m2 of insulation
| Double glazing | m2 of windows
| Use of highly energy efficient equipment bought | Equipment number
| Area covered with sensors and timers | m2
| Area with shadings installed | m2
| Installation of digital thermostats | Number of thermostats
| Average temperature in buildings | oC
| Solar water heaters installed | Number of solar water heaters
| A/Cs replaced with new more efficienct ones | Number of A/Cs
| Surface with cool colors applied | m2
| Buildings using cool colors | Number of buildings
| Buildings fully/partially refurbished | Number of buildings
Other public infrastructure | Street lighting lamps replaced with LEDs (per area/total) | Number of lamps
| Length of new lighting network | km
Energy supply | Length of new gas pipelines | km
| District heating plants | Number of plants
| Installed renewable energy capacity | KW
Other | Awareness raising campaigns/activities/events for students/residents | Number of campaigns/activities/events
| Students/residents reached by campaigns/activities/events | Number of students/residents attending each event
| Training seminars implemented | Number of seminars
| Municipal/regional employees trained | Number of employees
| Printed informational material | Number of material distributed
| Participation in funding programs | Number of programs

## Actions Monitoring_Example
Monitoring Template
Actions Monitoring (Example)
This is an example of how to fill in the table with the actions monitored.
Actions | Status (drop-down list) | Duration |  |  |  | Budget |  | Energy savings |  | Renewable Energy Sources (RES) |  | Other impacts e.g. jobs created | Main barriers (if any) | Indicators | [5 empty] | Other comments
|  | Estimated start | Actual start | Estimated end date | Actual end date | Estimated budget (Euros) | Cost spent so far (Euros) | Energy savings targets (KWh) | Actual energy savings (KWh) | RES production targets (KWh) | Actual RES production (KWh) |  |  | Type of key indicator monitored | Achievement until now | Type of key indicator monitored | Achievement until now | Type of key indicator monitored | Achievement until now
Energy upgrade of the 1st, 3rd and 6th high school of Municipality of *** | Completed | February 2020 | 2020-02-18 | August 2020 | 2020-10-01 | 300000 | 300000 | 6000 | 5500 |  |  |  | Delays due to bureaucracy | Number of new heating systems (natural gas) | 3 | Double glazing | 150 m^2 | Number of lamps replaced with LEDs | 52
Thermal insulation in selected public buildings in the region of *** | Ongoing | June 2022 | 2020-07-01 | December 2023 | Ongoing | 1000000 | 700000 | 100000 |  |  |  | -Employees noted an improvement in thermal comfort -Estimated that three municipal halls reduced the use of their heating system |  | Number of buildings with new insulation | 23/35
Solar water heaters in 6 indoor gyms | Future | March 2024 |  | June 2024 |  | 5000 |  | 1500 |  | 1500 |  |  |  | Number of solar water heaters
Replacement of old ACs with new in 5 municipal halls | Canceled | March 2024 | [10 empty] | Canceled due to the lack of funding
Awareness raising campaign in schools for energy savings | Postponed for later | September 2023 New estimation: January 2024 |  | June 2024 New estimation: December 2024 |  | 10000 |  | No direct energy savings |  | 1500 |  |  | Postponed due to the lack of human resources | Number of students informed |  | Number of schools where campaigns took place
Total number of Actions
Completed | 1
Ongoing | 1
About to start | 0 |  | Graphic Results (example)
Postponed for later | 1
Future | 1
Canceled | 1
Total | 5

## Index (hidden)
Index
Status
Completed
Ongoing
About to start
Postponed for later
Future
Canceled